## CACoP Forum work plan
CACoP Forum work plan |  | Last reviewed: | December 2023
REF | WORK ITEM | OWNER | RAISED | START DATE | DUE DATE | STATUS | PROGRESS UPDATES | NOTES/COMMENTS
CFWI-001 | Produce a set of diagrams showing the relationship between Codes | REC | 2022-10-11 | 2022-10-11 | 2023-01-31 | Closed | Dec 22: Draft diagrams have been shared with the Supplier that raised this request, who was supportive of these. These diagrams will be updated before being published on the CACoP website. Feb 23: The updated diagrams have been shared with the Forum for final comment. Following this, these will be finalised and published on the CACoP website. Apr 23: These diagrams have now been published on the CACoP website.
CFWI-002 | Forum engagement and input on Code Reform | Chair | 2023-02-14 | 2023-02-14 | Ongoing | Open | Feb 23: The Forum and Ofgem discussed how the Forum could input and be engaged on Code Reform. Ofgem will engage the Forum ahead of its next RFI on Code Reform. The Forum also agreed to consider and develop any initiatives that would support the principles of Code Reform and Consolidation over the coming months, and made this one of its objectives. Specific work items for each initiative will be added as they arise.
CFWI-003 | Consolidation of cross-Code change discussions into CCSG by expanding CCSG membership to all CACoP Codes | Chair / REC | 2023-02-14 | 2023-02-14 | 2023-04-11 | Closed | Feb 23: The Forum agreed to proceed with investigating this. The Chair will liaise with the CCSG Chair, Ofgem and the relevant Code Administrators to discuss this proposal further and seek views on taking this forward, and will report back to the Forum in April. Apr 23: Following investigations and discussions with the relevant Codes, the Forum agreed there is not a strong business case for the remaining CACoP Codes becoming CCSG members.
CFWI-004 | Consider and develop initiatives and approaches that will support the end consumer and the policy positions of consumer advisory and focus groups | All Forum members | 2023-02-14 | 2023-02-14 | Ongoing | Open | Feb 23: The Forum considered it should monitor the policy positions of advisory or focus groups related to end consumers, and consider whether it can implement any initiatives or approaches to support with these. All Forum members will be responsible for putting forward potential initiatives arising from this. Specific work items for each initiative will be added as they arise.
CFWI-005 | Complete a review of the CACoP document and present any changes to Ofgem for approval | SEC | 2023-02-14 | 2023-06-13 | 2023-12-31 | Open | Feb 23: The Forum agreed to undertake a review of the CACoP document in 2023. Dates for this review will be confirmed at a later meeting. Apr 23: This review is proposed to commence in the Summer. A paper setting out the proposed approach will be brought to the June 2023 Forum meeting. Jun 23: The Forum agreed the scope and approach for the review. The results of the survey will be brought to the October 2023 Forum meeting. Aug 23: The consultation and draft changes to the CACoP have been prepared and circulated for comment. The Forum is further reviewing the modification timelines et out in the CACoP document. Once this has been completed, the survey will be issued in early September 2023. Oct 23: The survey has been issued and will close on 27 October 2023. The responses will be discussed at the December Forum meeting. Dec 23: The Forum agreed the proposed changes to be recommended to Ofgem, and submitted these for approval.
CFWI-006 | Provide support and input for the Open Data and Consumer Consent project | REC | 2023-02-14 | 2023-04-11 | 2023-10-06 | Closed | Feb 23: The Forum received an update from RECCo on its digitalisation principles. The Chair agreed to work with RECCo and the REC to understand whether and how the Forum can support with engagement on the work around open data and consumer consent with all the Codes. Apr 23: RECCo will be hosting a workshop with the Code Administrators, expected to happen in early June. The Forum will consider what further support it can provide based on the outcomes of that workshop. Jun 23: The workshop was held on 6 June 2023. The Chair is liaising with RECCo to confirm any further support the Forum can provide on this work. Aug 23: An update on this project was provided at the August Forum meeting, with a further update to be provided in October. No further input from the Forum has been sought at this stage. Oct 23: An update on the project was provided at the October Forum meeting. The Forum and RECCo agreed there is no further support the Fiorum can provide on this. | The Forum agreed to review the outcomes of the two associated REC Change Proposals in late 2024, to understand if there is benefit in other Codes making similar changes based on the outcomes of the REC changes.
CFWI-007 | Review the CACoP website performance statistics | Chair | 2023-04-11 | 2023-04-11 | 2023-12-31 | Closed | Apr 23: The Forum agreed to review the website's performance, including the download statistics for key documents. Further actions will be determined once those statistics have been reviewed. Jun 23: The Forum reviewed the available statistics and agreed some immediate enhancements to take forward to make the news sections more visible. Further input will be sought from Code Parties through the survey being conducted under CFWI-005. Dec 23: The Forum did not propose any further changes following its review of the CACoP survey responses.
CFWI-008 | Develop common questions for Code Administrators' customer surveys | BSC | 2023-04-11 | 2023-04-11 | 2023-06-13 | Closed | Apr 23: The Forum noted previous work carried out to develop some common questions that Code Administrators could include in their customer surveys, and that this should be completed. Jun 23: The Forum reviewed the previous work, and concluded that no common questions had been agreed to take forward, and so there is no further work to complete. | The Forum noted that each Code already has sets of questions that are relevant to how each operates, and that keeping these unchanged helps with year-on-year comparisons. The Forum saw little overall benefit from aligning these questions.
CFWI-009 | Share best practice approaches for Code Party and distibution lists | DCUSA | 2023-08-15 | 2023-10-06 | TBC | Open | Aug 23: The Forum agreed to look at the approaches taken around managing the lists of Code Parties and the distribution lists for communications to share best practice on these. Oct 23: The Forum agreed to discuss this at the December Forum meeting once further information has been circulated by the DCUSA and the other Codes have had a chance to consider this. Dec 23: Due to workload and availability, this discussion will be held at a future Forum meeting.
CFWI-010 | Review the CACoP Forum membership and whether this should be expanded beyond the Code Administrators subject to the CACoP | TBC | 2023-12-01 | TBC | TBC | Pending | Dec 23: The Forum agreed to consider whether the Forum's membership should be expanded beyond the Code Administrators subject to the CACoP.
CFWI-011 | Consider a more consistent approach to Code Administrators' customer surveys | TBC | 2023-12-01 | TBC | TBC | Pending | Dec 23: Following its announcement there won't be an Ofgem-led cross-Code survey, Ofgem proposed that Code Administrators could carry out their own surveys, with the Forum agreeing more consistent questions that could be asked through these. The Forum agreed to consider this, including how this could work and any common questions. | Follows on from CFWI-008